## Sheet1
MAVISBANK POLICIES: RISK ASSESSMENT
rev 4: Date: 11.2.2016
Area | Location | Hazard | Who might be harmed? | Action currently being taken to control risk | Proposed action & timescale for implementation | Action by whom | Action by when | Progress | Date Completed
GENERAL
Landslip area to NE corner of Estate | Zone 1 as shown on Drawing D.01 (titled H&S Zoning Plan) | Ground slippage next to existing track. Drop of up to 2.9 m with continuing gradual ground movement. The most significant slip plane goes just beyond the boundary fence over a short section about 20 m to the west of the dovecot, cutting off the track along the inside of the boundary fence. | General public Dog walkers Locals and adjacent land owners /neighbours Farm workers | Engineering land survey completed Feb 2013. Monitored annually by Engineers following initial bi-annual reports and at least fortnightly by MCU. Reports analysed and measures adapted as required Walkers are discouraged from using the informal track along the north boundary fence with warning signage erected at entry points to paths. (Plastic barriers proved to be ineffectual) | Information regarding risk to be distributed to users through local press, radio and internet | Communications Team/ P Ranson | Update to be issued based on Jan 2015 Engineer's report & Risk Assessment visit Nov 2015 | In progress | tbc
[5 empty] | Information passed to local residents/local groups by direct e-mail | P Ranson | Update to be issued based Jan 2015 Engineer's report & Risk Assessment visit Nov 2015 | In progress | tbc
[5 empty] | Summary of surveys and monitoring reports to be issued to relevant parties for dissemination & use on websites etc | P Ranson | J Turner to provide updates annually | Latest full survey report dated 22 May 2014 | on-going
[5 empty] | HES Website to be updated re site conditions & risk to users | Communications Team/ P Ranson | The site is NOT advertised on our website as a site open to visitors but public footpaths have been installed by Mavisbank Trust in April 2014 | Update required for website | tbc
LOCATION SPECIFIC
Area around Dovecot | Zone 1A as shown on Drawing D.01 (titled H&S Zoning Plan) | The near vertical face at the top of the slip plane is now gradually eroding back to form a more stable slope. There is a danger that the edge will give way if anyone goes too close. Jan/Feb 2016. A further survey shows little change to the ground profile adjacent to the dovecot and also minimal change on the alignment of the dovecot. JAN 15 report: this survey records no movement in the Doocot since the previous survey of Jan 2014. JAN 14 report: This survey shows no movement of the Dovecot from July 2013 to date. The slip plane was 3 m south of the dovecot but the raw face is eroding back toward the dovecot and is now 200 mm closer at the surface. The ground on the lower side of the slip plane appears to have dropped about 1.5 m to date (compared to contours on the topographical survey). There is evidence of continuing movement of the ground adjacent to the low side of the slip plane. | Building could be made structurally unstable in any landslip. This is likely to affect anyone in the immediate vicinity at the time of the collapse e.g. General public/dog walkers, etc. | Monitoring continues annually in winter months by Engineers, and at least fortnightly by MCU. . | Engineers have prepared costed Options Appraisal that sets down choices available. Further detail to costings to be obtained in order to allow more accurate assessment of resources required for each option | P Ranson | Engineer's report was discussed on 2014 AMA and the decision was made to remove temporary barriers which are being continually trampled down and upgrade signage at entrance to paths from advisory to prohibitive | Signage modification on site completed. | 2015-02-01
[6 empty] | J Turner | Options Appraisal recommended works required to be costed | Completed | 2015-11-24
[5 empty] | Carry out Laser scan of Doocot to record existing fabric | P Ranson | Laser Scan | Completed | Feb-12
[5 empty] | Assessment of Significance of Doocot completed | J Anderson | Mavisbank Doocot Provisional Assessment of Significance | Completed | 2013-12-05
[5 empty] | Ground investigation | J Turner | Test bores to determine ground strata and suitability for ground stabilisation | As funds permit | tba
[5 empty] | Check on ground movements over wider are near to dovecote | Engineer/ Architectural technicians | Further laser survey of wider area near to dovecote | In progress | Feb 2016
Boggy/ waterlogged ground | Zone 2 as shown on Drawing D.01 (titled H&S Zoning Plan) | Water is drained onto already saturated ground causing it to become waterlogged. This is increasing the potential for landslips and increasing the likelihood of an accident when moving across the area | Land is difficult to walk across for General public; Dog walkers; Workers, etc. Plant species changing due to waterlogging | Extent of waterlogged ground monitored as part of AMA; Wherever possible localised small scale interventions carried out as necessary to increase drainage run off onto established watercourses. | Design and implement drainage scheme to reduce standing water on ground. | J Turner | Carry out test bores to confirm ground strata across site. Following this develop scheme of drainage works across site. | As funding permits | tba
Open Water | Zone 3 as shown on Drawing D.01 (titled H&S Zoning Plan) | Open water and area encroached by reeds with hidden edges to water | General public/dog walkers/etc, i.e. anyone unfamiliar with the site and its hazards | It is assumed visitors to the site unfamiliar with it take their own precautions when venturing off the existing paths | Management of the existing reeds to allow the area of open water to be read more easily (and to restore the original design intention) | P Ranson | Include reed clearance in future management works following necessary wildlife surveys. | As funding permits | tba
Woodland | Zone 4 as shown on Drawing D.01 (titled H&S Zoning Plan) | Areas consist of mixed broadleaf species with heritage trees amongst them. Terrain varies, falling limbs, branches, trees. | General public/dog walkers/etc, i.e. anyone unfamiliar with the site and its hazards | It is assumed visitors to the site unfamiliar with it take their own precautions when venturing off the existing paths | Management of the woodland areas including maintenance of key trees in order to maintain the historic design intention | P Ranson | Include woodland management in future management works following necessary wildlife surveys. | As funding permits | tba
Fenced off Hazard | Zone 5 as shown on Drawing D.01 (titled H&S Zoning Plan) | Area of localised collapse possibly due to collapse of culvert | General public/dog walkers/etc, i.e. anyone who ignores the warning signage and fence. | Area fenced off and warning signage erected. Area inspected at least fortnightly by MCU. | Further drainage investigation to establish current/historic drainage prior to Carrying out repairs, backfilling the 'hole' and re-seeding the ground | J Turner | Carry out further investigation to establish current/historic drainage in this location | In progress | 2016-10-01
Grassland | Zone 6 as shown on Drawing D.01 (titled H&S Zoning Plan) | Terrain varies | General public/dog walkers/etc. | Area mown annually and invasive species treated annually | Continue present mowing regime and annual treatment of invasive species | P Ranson | Continue present mowing regime and annual treatment of invasive species | In progress | On-going
Key | HES | Historic Environment Scotland
| VO | Visitor Operations
| MCU | Monument Conservation Unit
| AMA | Annual Monument Audit
Revisions
Version 3 | 11.01.16 | reviewed
Version 4 | 11.02.16 | reviewed

## Version Control
Version | Date | By | Details of amendments
Version 1 | 05.11.13 | JR | JR initial DRAFT
Version 2 | 13.02.14 | PR | PR input
Version 3 | 24.06.14 | PR | PR input
Version 4 | 05.11.15 | PR | PR input

## Compatibility Report
Compatibility Report for Mavisbank_RA_20151105.xls
Run on 05/11/2015 17:26
The following features in this workbook are not supported by earlier versions of Excel. These features may be lost or degraded when opening this workbook in an earlier version of Excel or if you save this workbook in an earlier file format.
Minor loss of fidelity | # of occurrences | Version
An embedded object in this worksheet is created in a newer version of Office. You cannot edit it in an earlier version of Excel. | 1 | Excel 97-2003